## 1 Meter Install Forecast-Est's
Appendix 6 - SAWS Connect H2O AMI Water Deployment Plan | [9 empty] | NO EPI VENDOR DATA ENTRY TO BE PERFORMED ON THIS SHEET. | [8 empty] | 2023-02-14
Meter Installation Forecast & Projections
THESE METER COUNTS ARE BASED ON BEST INFORMATION CURRENTLY AVAILABLE. | [8 empty] | Scenario 1: End 6.30.26: |  |  | ESTIMATED INSTALLS BY METER SIZE AND YEAR.
THESE NUMBERS ARE, HOWEVER, SUBJECT TO VARIATION AND CHANGE. | [8 empty] | BASED ON INSTALLATION RUN RATES FROM TAB '2 FSWD Scenario 1, End 6.30.26'.
References to Meters herein includes installation of both Meters and their associated EndPoints.
[9 empty] | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | Totals
| 2022 | ALL | 5/8 - 2" | 3 - 10" | SAWS | Vendor | Vendor |  | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor
Meter Size | Est'd Qty | Meters | Meters | Meters | Installs | Installs | Installs |  | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs
| note 3 | %'s | %'s | %'s | 5/8 - 2" | 5/8 - 2" | 3" - 10" |  | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 10"
5/8" | 498460.2232 | 87.59% | 87.94% |  | 42209.0434 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3/4" | 37140.2279 | 6.526% | 6.552% |  | 3144.9922 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1" | 15993.4658 | 2.81% | 2.821% |  | 1354.3084 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1-1/2" | 8879.1273 | 1.56% | 1.566% |  | 751.8744 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
2" | 6374.4554 | 1.12% | 1.125% |  | 539.7816 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3" | 1114 | 0.1957% |  | 49.56% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
4" | 678 | 0.1191% |  | 30.16% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
6" | 337 | 0.05922% |  | 14.99% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
8" | 96 | 0.01687% |  | 4.27% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
10" | 23 | 0.004042% |  | 1.023% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Other | 0 | 0% |  | 0% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Totals | 569095.4996 | 100% | 100% | 100% | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[5 empty] | TRUE | TRUE | TRUE | 0 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
note 3: These are the estimated quantity of meters that exist & require replacement | [5 empty] | FALSE | FALSE
by EPI/SAWS, plus installation of new AMI communications modules, as of end of 1.31.23. | [5 empty] | Total: | 0 | FALSE | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | 0
THESE METER COUNTS ARE BASED ON BEST INFORMATION CURRENTLY AVAILABLE. | [8 empty] | Scenario 2: End 12.31.26: |  |  | ESTIMATED INSTALLS BY METER SIZE AND YEAR.
THESE NUMBERS ARE, HOWEVER, SUBJECT TO VARIATION AND CHANGE. | [8 empty] | BASED ON INSTALLATION RUN RATES FROM TAB '2 FSWD Scenario 2, End 12.31.26'.
References to Meters herein includes installation of both Meters and their associated EndPoints.
[9 empty] | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2026 |  | Totals
| 2022 | ALL | 5/8 - 2" | 3 - 10" | SAWS | Vendor | Vendor |  | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor
Meter Size | Est'd Qty | Meters | Meters | Meters | Installs | Installs | Installs |  | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs
| note 3 | %'s | %'s | %'s | 5/8 - 2" | 5/8 - 2" | 3" - 10" |  | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 10"
5/8" | 498460.2232 | 87.59% | 87.94% |  | 42209.0434 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3/4" | 37140.2279 | 6.526% | 6.552% |  | 3144.9922 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1" | 15993.4658 | 2.81% | 2.821% |  | 1354.3084 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1-1/2" | 8879.1273 | 1.56% | 1.566% |  | 751.8744 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
2" | 6374.4554 | 1.12% | 1.125% |  | 539.7816 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3" | 1114 | 0.1957% |  | 49.56% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
4" | 678 | 0.1191% |  | 30.16% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
6" | 337 | 0.05922% |  | 14.99% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
8" | 96 | 0.01687% |  | 4.27% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
10" | 23 | 0.004042% |  | 1.023% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Other | 0 | 0% |  | 0% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Totals | 569095.4996 | 100% | 100% | 100% | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[5 empty] | TRUE | TRUE | TRUE | 0 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
note 3: These are the estimated quantity of meters that exist & require replacement | [5 empty] | FALSE | FALSE
by EPI/SAWS, plus installation of new AMI communications modules, as of end of 1.31.23. | [5 empty] | Total: | 0 | FALSE | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | 0
THESE METER COUNTS ARE BASED ON BEST INFORMATION CURRENTLY AVAILABLE. | [8 empty] | Scenario 3: End 6.30.27: |  |  | ESTIMATED INSTALLS BY METER SIZE AND YEAR.
THESE NUMBERS ARE, HOWEVER, SUBJECT TO VARIATION AND CHANGE. | [8 empty] | BASED ON INSTALLATION RUN RATES FROM TAB '2 FSWD Scenario 3, End 6.30.27'.
References to Meters herein includes installation of both Meters and their associated EndPoints.
[9 empty] | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2026 |  | Totals
| 2022 | ALL | 5/8 - 2" | 3 - 10" | SAWS | Vendor | Vendor |  | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor
Meter Size | Est'd Qty | Meters | Meters | Meters | Installs | Installs | Installs |  | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs
| note 3 | %'s | %'s | %'s | 5/8 - 2" | 5/8 - 2" | 3" - 10" |  | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 10"
5/8" | 498460.2232 | 87.59% | 87.94% |  | 42209.0434 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3/4" | 37140.2279 | 6.526% | 6.552% |  | 3144.9922 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1" | 15993.4658 | 2.81% | 2.821% |  | 1354.3084 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1-1/2" | 8879.1273 | 1.56% | 1.566% |  | 751.8744 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
2" | 6374.4554 | 1.12% | 1.125% |  | 539.7816 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3" | 1114 | 0.1957% |  | 49.56% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
4" | 678 | 0.1191% |  | 30.16% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
6" | 337 | 0.05922% |  | 14.99% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
8" | 96 | 0.01687% |  | 4.27% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
10" | 23 | 0.004042% |  | 1.023% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Other | 0 | 0% |  | 0% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Totals | 569095.4996 | 100% | 100% | 100% | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[5 empty] | TRUE | TRUE | TRUE | 0 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
note 3: These are the estimated quantity of meters that exist & require replacement | [5 empty] | FALSE | FALSE
by EPI/SAWS, plus installation of new AMI communications modules, as of end of 1.31.23. | [5 empty] | Total: | 0 | FALSE | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | 0

## 2 FSWD Scenario 1, End 6.30.26
Full System Wide Deployment |  |  |  |  | 2023-02-14 |  | Appendix 6 - SAWS Connect H2O AMI Water Deployment Plan - Scenario 1 - End 6.30.2026
References to Meters herein includes installation of both Meters and their associated EndPoints.
| Yellow Cell: EPI Vendor to provide Data. | [8 empty] | 8 | EPI Vendor to Provide its planned # of Field Installers per Field Supervisor.
[6 empty] | 15 | [10 empty] | (EPI Contract Total Qty)
|  |  |  | Installs by Others - Actuals |  | SAWS Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  | EPI Vendor - New Installs | TOTAL - ALL Installers - Planned |  |  | Qty Installs
|  |  |  | 5/8 - 2" Meters |  | 5/8 - 2" Meters Only |  |  |  | 5/8 - 2" Meters Only |  |  |  | 3" - 10" Meters Only (Note 1) |  |  | Total - All Meters | 5/8 - 10" Meters |  |  | by Year
| Mo-Yr | FSWD Deploy- ment Mo. # | Vendor Deploy- ment Mo. # | Avg. meters per month - all persons | Cumulative meters - all persons | Estimated Avg Installers per day | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. Number of Installers, this Month | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. meters per week - all Crew | Avg. meters per month - all persons | Cumulative meters - all persons | Cumulative meters - all persons | Total Avg. meters per day - all persons | Total Avg. meters per month - all persons | Cumulative Total meters - all persons | [Project Only; excludes New Bus. & Maint.]
AMI/MDMS | 2022-01-01
Phase 3 - FSWD | 2022-02-01
2022-03-01
2022-04-01
| 2022-05-01 | 1 |  | 1077 | 1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077 | 1077
| 2022-06-01 | 2 |  | 1989 | 3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989 | 3066
| 2022-07-01 | 3 |  | 3083 | 6149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083 | 6149
| 2022-08-01 | 4 |  | 6884 | 13033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6884 | 13033
| 2022-09-01 | 5 |  | 7774 | 20807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7774 | 20807
| 2022-10-01 | 6 |  | 3594 | 24401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3594 | 24401
| 2022-11-01 | 7 |  | 3194 | 27595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194 | 27595
| 2022-12-01 | 8 |  | 7160 | 34755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7160 | 34755 | 34755
AMI/MDMS | 2023-01-01 | 9 |  | 4702 | 39457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4702 | 39457
Phase 3 - FSWD | 2023-02-01 | 10 |  | 0 | 39457 | 13 | 195 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 43357
(cont'd) | 2023-03-01 | 11 |  | 0 | 39457 | 13 | 195 | 3900 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 47257
| 2023-04-01 | 12 |  | 0 | 39457 | 13 | 195 | 3900 | 11700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 51157
| 2023-05-01 | 13 |  | 0 | 39457 | 13 | 195 | 3900 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 55057
| 2023-06-01 | 14 |  | 0 | 39457 | 13 | 195 | 3900 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 58957
| 2023-07-01 | 15 |  | 0 | 39457 | 13 | 195 | 3900 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 62857
| 2023-08-01 | 16 |  | 0 | 39457 | 13 | 195 | 3900 | 27300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 66757
| 2023-09-01 | 17 |  | 0 | 39457 | 13 | 195 | 3900 | 31200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 70657
| 2023-10-01 | 18 |  | 0 | 39457 | 13 | 195 | 3900 | 35100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 74557
| 2023-11-01 | 19 | 1 | 0 | 39457 | 13 | 195 | 3900 | 39000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 78457
| 2023-12-01 | 20 | 2 | 0 | 39457 | 13 | 195 | 3900 | 42900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 82357 | 47602
AMI/MDMS | 2024-01-01 | 21 | 3 | 0 | 39457 | 7 | 105 | 2100 | 45000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 84457
Phase 3 - FSWD | 2024-02-01 | 22 | 4 | 0 | 39457 | 7 | 105 | 2100 | 47100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 86557
(cont'd) | 2024-03-01 | 23 | 5 | 0 | 39457 | 3 | 45 | 900 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 900 | 87457
| 2024-04-01 | 24 | 6 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-05-01 | 25 | 7 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-06-01 | 26 | 8 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-07-01 | 27 | 9 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-08-01 | 28 | 10 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-09-01 | 29 | 11 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-10-01 | 30 | 12 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-11-01 | 31 | 13 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-12-01 | 32 | 14 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 5100
AMI/MDMS | 2025-01-01 | 33 | 15 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2025-02-01 | 34 | 16 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2025-03-01 | 35 | 17 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-04-01 | 36 | 18 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-05-01 | 37 | 19 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-06-01 | 38 | 20 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-07-01 | 39 | 21 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-08-01 | 40 | 22 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-09-01 | 41 | 23 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-10-01 | 42 | 24 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-11-01 | 43 | 25 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-12-01 | 44 | 26 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2026-01-01 | 45 | 27 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2026-02-01 | 46 | 28 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2026-03-01 | 47 | 29 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-04-01 | 48 | 30 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-05-01 | 49 | 31 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-06-01 | 50 | 32 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-07-01 | 51 | 33 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-08-01 | 52 | 34 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-09-01 | 53 | 35 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-10-01 | 54 | 36 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-11-01 | 55 | 37 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-12-01 | 56 | 38 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2027-01-01 | 57 | 39 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2027-02-01 | 58 | 40 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2027-03-01 | 59 | 41 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-04-01 | 60 | 42 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-05-01 | 61 | 43 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-06-01 | 62 | 44 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-07-01 | 63 | 45 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-08-01 | 64 | 46 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-09-01 | 65 | 47 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-10-01 | 66 | 48 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-11-01 | 67 | 49 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-12-01 | 68 | 50 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457 | 0
[7 empty] | Set-aside - Reserved | excludes | 53607 |  |  | EPI Vendor Qty Must Be: | 430800 |  | EPI Vendor Qty Must Be: | 2248 | 433048 |  |  |  | 87457
[7 empty] | SAWS Qty: | remaining | 48000 |  |  |  |  | Note 1: Option to assign these to |  |  | EPI Total Qty Must Be: 433,048 |  |  | Set-aside - Reserved | 53607
[14 empty] | EPI is at SAWS' Discretion. | [5 empty] | Total | 141064
Start no earlier than Sep-24
Start Ramp in Nov-23

## 2 FSWD Scenario 2, End 12.31.26
Full System Wide Deployment |  |  |  |  | 2023-02-14 |  | Appendix 6 - SAWS Connect H2O AMI Water Deployment Plan - Scenario 2 - End 12.31.2026
References to Meters herein includes installation of both Meters and their associated EndPoints.
| Yellow Cell: EPI Vendor to provide Data. | [8 empty] | 8 | EPI Vendor to Provide its planned # of Field Installers per Field Supervisor.
[6 empty] | 15 | [10 empty] | (EPI Contract Total Qty)
|  |  |  | Installs by Others - Actuals |  | SAWS Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  | EPI Vendor - New Installs | TOTAL - ALL Installers - Planned |  |  | Qty Installs
|  |  |  | 5/8 - 2" Meters |  | 5/8 - 2" Meters Only |  |  |  | 5/8 - 2" Meters Only |  |  |  | 3" - 10" Meters Only (Note 1) |  |  | Total - All Meters | 5/8 - 10" Meters |  |  | by Year
| Mo-Yr | FSWD Deploy- ment Mo. # | Vendor Deploy- ment Mo. # | Avg. meters per month - all persons | Cumulative meters - all persons | Estimated Avg Installers per day | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. Number of Installers, this Month | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. meters per week - all Crews | Avg. meters per month - all persons | Cumulative meters - all persons | Cumulative meters - all persons | Total Avg. meters per day - all persons | Total Avg. meters per month - all persons | Cumulative Total meters - all persons | [Project Only; excludes New Bus. & Maint.]
AMI/MDMS | 2022-01-01
Phase 3 - FSWD | 2022-02-01
2022-03-01
2022-04-01
| 2022-05-01 | 1 |  | 1077 | 1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077 | 1077
| 2022-06-01 | 2 |  | 1989 | 3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989 | 3066
| 2022-07-01 | 3 |  | 3083 | 6149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083 | 6149
| 2022-08-01 | 4 |  | 6884 | 13033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6884 | 13033
| 2022-09-01 | 5 |  | 7774 | 20807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7774 | 20807
| 2022-10-01 | 6 |  | 3594 | 24401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3594 | 24401
| 2022-11-01 | 7 |  | 3194 | 27595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194 | 27595
| 2022-12-01 | 8 |  | 7160 | 34755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7160 | 34755 | 34755
AMI/MDMS | 2023-01-01 | 9 |  | 4702 | 39457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4702 | 39457
Phase 3 - FSWD | 2023-02-01 | 10 |  | 0 | 39457 | 13 | 195 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 43357
(cont'd) | 2023-03-01 | 11 |  | 0 | 39457 | 13 | 195 | 3900 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 47257
| 2023-04-01 | 12 |  | 0 | 39457 | 13 | 195 | 3900 | 11700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 51157
| 2023-05-01 | 13 |  | 0 | 39457 | 13 | 195 | 3900 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 55057
| 2023-06-01 | 14 |  | 0 | 39457 | 13 | 195 | 3900 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 58957
| 2023-07-01 | 15 |  | 0 | 39457 | 13 | 195 | 3900 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 62857
| 2023-08-01 | 16 |  | 0 | 39457 | 13 | 195 | 3900 | 27300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 66757
| 2023-09-01 | 17 |  | 0 | 39457 | 13 | 195 | 3900 | 31200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 70657
| 2023-10-01 | 18 |  | 0 | 39457 | 13 | 195 | 3900 | 35100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 74557
| 2023-11-01 | 19 | 1 | 0 | 39457 | 13 | 195 | 3900 | 39000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 78457
| 2023-12-01 | 20 | 2 | 0 | 39457 | 13 | 195 | 3900 | 42900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 82357 | 47602
AMI/MDMS | 2024-01-01 | 21 | 3 | 0 | 39457 | 7 | 105 | 2100 | 45000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 84457
Phase 3 - FSWD | 2024-02-01 | 22 | 4 | 0 | 39457 | 7 | 105 | 2100 | 47100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 86557
(cont'd) | 2024-03-01 | 23 | 5 | 0 | 39457 | 3 | 45 | 900 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 900 | 87457
| 2024-04-01 | 24 | 6 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-05-01 | 25 | 7 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-06-01 | 26 | 8 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-07-01 | 27 | 9 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-08-01 | 28 | 10 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-09-01 | 29 | 11 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-10-01 | 30 | 12 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-11-01 | 31 | 13 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-12-01 | 32 | 14 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 5100
AMI/MDMS | 2025-01-01 | 33 | 15 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2025-02-01 | 34 | 16 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2025-03-01 | 35 | 17 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-04-01 | 36 | 18 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-05-01 | 37 | 19 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-06-01 | 38 | 20 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-07-01 | 39 | 21 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-08-01 | 40 | 22 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-09-01 | 41 | 23 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-10-01 | 42 | 24 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-11-01 | 43 | 25 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-12-01 | 44 | 26 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2026-01-01 | 45 | 27 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2026-02-01 | 46 | 28 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2026-03-01 | 47 | 29 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-04-01 | 48 | 30 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-05-01 | 49 | 31 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-06-01 | 50 | 32 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-07-01 | 51 | 33 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-08-01 | 52 | 34 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-09-01 | 53 | 35 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-10-01 | 54 | 36 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-11-01 | 55 | 37 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-12-01 | 56 | 38 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2027-01-01 | 57 | 39 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2027-02-01 | 58 | 40 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2027-03-01 | 59 | 41 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-04-01 | 60 | 42 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-05-01 | 61 | 43 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-06-01 | 62 | 44 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-07-01 | 63 | 45 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-08-01 | 64 | 46 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-09-01 | 65 | 47 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-10-01 | 66 | 48 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-11-01 | 67 | 49 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-12-01 | 68 | 50 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457 | 0
[7 empty] | Set-aside - Reserved | excludes | 53607 |  |  | EPI Vendor Qty Must Be: | 430800 |  | EPI Vendor Qty Must Be: | 2248 | 433048 |  |  |  | 87457
[7 empty] | SAWS Qty: | remaining | 48000 |  |  |  |  | Note 1: Option to assign these to |  |  | EPI Total Qty Must Be: 433,048 |  |  | Set-aside - Reserved | 53607
[14 empty] | EPI is at SAWS' Discretion. | [5 empty] | Total | 141064
Start no earlier than Sep-24
Start Ramp in Nov-23

## 2 FSWD Scenario 3, End 6.30.27
Full System Wide Deployment |  |  |  |  | 2023-02-14 |  | Appendix 6 - SAWS Connect H2O AMI Water Deployment Plan - Scenario 3 - End 6.30.27
References to Meters herein includes installation of both Meters and their associated EndPoints.
| Yellow Cell: EPI Vendor to provide Data. | [8 empty] | 8 | EPI Vendor to Provide its planned # of Field Installers per Field Supervisor.
[6 empty] | 15 | [10 empty] | (EPI Contract Total Qty)
|  |  |  | Installs by Others - Actuals |  | SAWS Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  | EPI Vendor - New Installs | TOTAL - ALL Installers - Planned |  |  | Qty Installs
|  |  |  | 5/8 - 2" Meters |  | 5/8 - 2" Meters Only |  |  |  | 5/8 - 2" Meters Only |  |  |  | 3" - 10" Meters Only (Note 1) |  |  | Total - All Meters | 5/8 - 10" Meters |  |  | by Year
| Mo-Yr | FSWD Deploy- ment Mo. # | Vendor Deploy- ment Mo. # | Avg. meters per month - all persons | Cumulative meters - all persons | Estimated Avg Installers per day | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. Number of Installers, this Month | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. meters per week - all Crews | Avg. meters per month - all persons | Cumulative meters - all persons | Cumulative meters - all persons | Total Avg. meters per day - all persons | Total Avg. meters per month - all persons | Cumulative Total meters - all persons | [Project Only; excludes New Bus. & Maint.]
AMI/MDMS | 2022-01-01
Phase 3 - FSWD | 2022-02-01
2022-03-01
2022-04-01
| 2022-05-01 | 1 |  | 1077 | 1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077 | 1077
| 2022-06-01 | 2 |  | 1989 | 3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989 | 3066
| 2022-07-01 | 3 |  | 3083 | 6149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083 | 6149
| 2022-08-01 | 4 |  | 6884 | 13033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6884 | 13033
| 2022-09-01 | 5 |  | 7774 | 20807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7774 | 20807
| 2022-10-01 | 6 |  | 3594 | 24401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3594 | 24401
| 2022-11-01 | 7 |  | 3194 | 27595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194 | 27595
| 2022-12-01 | 8 |  | 7160 | 34755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7160 | 34755 | 34755
AMI/MDMS | 2023-01-01 | 9 |  | 4702 | 39457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4702 | 39457
Phase 3 - FSWD | 2023-02-01 | 10 |  | 0 | 39457 | 13 | 195 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 43357
(cont'd) | 2023-03-01 | 11 |  | 0 | 39457 | 13 | 195 | 3900 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 47257
| 2023-04-01 | 12 |  | 0 | 39457 | 13 | 195 | 3900 | 11700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 51157
| 2023-05-01 | 13 |  | 0 | 39457 | 13 | 195 | 3900 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 55057
| 2023-06-01 | 14 |  | 0 | 39457 | 13 | 195 | 3900 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 58957
| 2023-07-01 | 15 |  | 0 | 39457 | 13 | 195 | 3900 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 62857
| 2023-08-01 | 16 |  | 0 | 39457 | 13 | 195 | 3900 | 27300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 66757
| 2023-09-01 | 17 |  | 0 | 39457 | 13 | 195 | 3900 | 31200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 70657
| 2023-10-01 | 18 |  | 0 | 39457 | 13 | 195 | 3900 | 35100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 74557
| 2023-11-01 | 19 | 1 | 0 | 39457 | 13 | 195 | 3900 | 39000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 78457
| 2023-12-01 | 20 | 2 | 0 | 39457 | 13 | 195 | 3900 | 42900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 82357 | 47602
AMI/MDMS | 2024-01-01 | 21 | 3 | 0 | 39457 | 7 | 105 | 2100 | 45000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 84457
Phase 3 - FSWD | 2024-02-01 | 22 | 4 | 0 | 39457 | 7 | 105 | 2100 | 47100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 86557
(cont'd) | 2024-03-01 | 23 | 5 | 0 | 39457 | 3 | 45 | 900 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 900 | 87457
| 2024-04-01 | 24 | 6 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-05-01 | 25 | 7 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-06-01 | 26 | 8 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-07-01 | 27 | 9 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-08-01 | 28 | 10 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-09-01 | 29 | 11 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-10-01 | 30 | 12 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-11-01 | 31 | 13 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-12-01 | 32 | 14 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 5100
AMI/MDMS | 2025-01-01 | 33 | 15 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2025-02-01 | 34 | 16 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2025-03-01 | 35 | 17 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-04-01 | 36 | 18 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-05-01 | 37 | 19 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-06-01 | 38 | 20 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-07-01 | 39 | 21 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-08-01 | 40 | 22 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-09-01 | 41 | 23 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-10-01 | 42 | 24 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-11-01 | 43 | 25 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-12-01 | 44 | 26 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2026-01-01 | 45 | 27 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2026-02-01 | 46 | 28 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2026-03-01 | 47 | 29 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-04-01 | 48 | 30 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-05-01 | 49 | 31 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-06-01 | 50 | 32 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-07-01 | 51 | 33 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-08-01 | 52 | 34 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-09-01 | 53 | 35 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-10-01 | 54 | 36 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-11-01 | 55 | 37 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-12-01 | 56 | 38 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2027-01-01 | 57 | 39 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2027-02-01 | 58 | 40 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2027-03-01 | 59 | 41 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-04-01 | 60 | 42 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-05-01 | 61 | 43 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-06-01 | 62 | 44 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-07-01 | 63 | 45 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-08-01 | 64 | 46 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-09-01 | 65 | 47 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-10-01 | 66 | 48 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-11-01 | 67 | 49 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-12-01 | 68 | 50 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457 | 0
[7 empty] | Set-aside - Reserved | excludes | 53607 |  |  | EPI Vendor Qty Must Be: | 430800 |  | EPI Vendor Qty Must Be: | 2248 | 433048 |  |  |  | 87457
[7 empty] | SAWS Qty: | remaining | 48000 |  |  |  |  | Note 1: Option to assign these to |  |  | EPI Total Qty Must Be: 433,048 |  |  | Set-aside - Reserved | 53607
[14 empty] | EPI is at SAWS' Discretion. | [5 empty] | Total | 141064
Start no earlier than Sep-24
Start Ramp in Nov-23

## 3 FSWD Graphs, Scenarios 1-3
Appendix 6 - SAWS ConnectH2O AMI Water Deployment Plan
Peak = 10,500 size 5/8 - 2", [plus addtl. 72 size 3" - 10"]
Peak = 15,500 size 5/8 - 2", [plus addtl. 120 size 3" - 10"]
Peak = 13,000 size 5/8 - 2", [plus addtl. 88 size 3" - 10"]