## 1. MTR Counts, Size-Age-OPTIONS
SAWS ConnectH2O Meter Counts by Size, Age & Meter Replacement Options | [11 empty] | 2019-11-11
BASELINE: | EXISTING METER DATA [DETAILS BY YEAR AT BOTTOM, BELOW]
Meter Age Years | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less
Meters age 2014 & Newer: |  | 193304.2232 | 10055.2279 | 6492.4658 | 3529.1273 | 2038.4554 | 317.8461 | 145.3619 | 87.393 | 23.8482 | 0.96963 | 215994.9185 | 215419.4996 | Note 2.
Meters age 2013 & Older: |  | 305156 | 27085 | 9501 | 5350 | 4336 | 901 | 717 | 368 | 107 | 32 | 353553 | 351428
Grand | Total: | 498460.2232 | 37140.2279 | 15993.4658 | 8879.1273 | 6374.4554 | 1218.8461 | 862.3619 | 455.393 | 130.8482 | 32.9696 | 569547.9185 | 566847.4996
SAWS ConnectH2O: Meter Replacement OPTIONS 1 Through 4:
OPTION 1: | KEEP ALL METERS AS-IS & RETROFIT WITH AMI COMMUNICATIONS MODULE ONLY. | [12 empty] | OPTION 1
Meter Age Years | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less
Grand | Total: | 498460.2232 | 37140.2279 | 15993.4658 | 8879.1273 | 6374.4554 | 1218.8461 | 862.3619 | 455.393 | 130.8482 | 32.9696 | 569547.9185 | 566847.4996 | Retain ALL AS-IS + Install/Retrofit with AMI Comms Module.
OPTION 2: | KEEP ALL METERS 2014 & NEWER AS-IS & RETROFIT WITH AMI COMMUNICATIONS MODULE ONLY. | [12 empty] | OPTION 2
REPLACE METERS 2013 & OLDER WITH NEW MECHANICAL MTRS & INSTALL AMI COMMUNICATIONS MODULE.
Meter Age Years | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less
Meters age 2014 & Newer: |  | 193304.2232 | 10055.2279 | 6492.4658 | 3529.1273 | 2038.4554 | 317.8461 | 145.3619 | 87.393 | 23.8482 | 0.96963 | 215994.9185 |  | Note 2. Retain AS-IS + Install/Retrofit with AMI Comms Module.
Meters age 2013 & Older: |  | 305156 | 27085 | 9501 | 5350 | 4336 | 901 | 717 | 368 | 107 | 32 | 353553 |  | Replace w/Mechanical Mtr + Install AMI Comms Module.
Grand | Total: | 498460.2232 | 37140.2279 | 15993.4658 | 8879.1273 | 6374.4554 | 1218.8461 | 862.3619 | 455.393 | 130.8482 | 32.9696 | 569547.9185 | 566847.4996
OPTION 3: | KEEP ALL METERS 2014 & NEWER AS-IS & RETROFIT WITH AMI COMMUNICATIONS MODULE ONLY. | [12 empty] | OPTION 3
REPLACE ALL METERS 2013 & OLDER WITH NEW STATIC MTRS & INSTALL AMI COMMUNICATIONS MODULE.
Meter Age Years | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less
Meters age 2014 & Newer: |  | 193304.2232 | 10055.2279 | 6492.4658 | 3529.1273 | 2038.4554 | 317.8461 | 145.3619 | 87.393 | 23.8482 | 0.96963 | 215994.9185 |  | Note 2. Retain AS-IS + Install/Retrofit with AMI Comms Module.
Meters age 2013 & Older: |  | 305156 | 27085 | 9501 | 5350 | 4336 | 901 | 717 | 368 | 107 | 32 | 353553 |  | Replace w/Static Mtr + Install AMI Comms Module
Grand | Total: | 498460.2232 | 37140.2279 | 15993.4658 | 8879.1273 | 6374.4554 | 1218.8461 | 862.3619 | 455.393 | 130.8482 | 32.9696 | 569547.9185 | 566847.4996
OPTION 4: | REPLACE ALL METERS WITH NEW STATIC MTRS & INSTALL AMI COMMUNICATIONS MODULE. | [12 empty] | OPTION 4
Meter Age Years | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less
Grand | Total: | 498460.2232 | 37140.2279 | 15993.4658 | 8879.1273 | 6374.4554 | 1218.8461 | 862.3619 | 455.393 | 130.8482 | 32.9696 | 569547.9185 | 566847.4996 | Replace ALL w/Static Mtr + Install AMI Comms Module
BASELINE: | EXISTING METER DATA - DETAILS
Meter Age Years | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less
Unknown (DSP) | <=2013 | 45967 | 9345 | 1302 | 488 | 84 | 67 | 54 | 17 | 7 |  | 57331 | 57186 | Note 1
0 | 2019 | 21337 |  | 619 | 215 | 240 | 42 | 29 | 14 | 2 |  | 22498 | 22411
1 | 2018 | 20825 | 1 | 607 | 400 | 230 | 33 | 10 | 10 | 1 |  | 22117 | 22063
2 | 2017 | 22940 | 3 | 1027 | 856 | 105 | 2 | 17 | 13 | 2 |  | 24965 | 24931
3 | 2016 | 21733 | 448 | 920 | 619 | 228 | 59 | 8 | 18 | 6 |  | 24039 | 23948
4 | 2015 | 43605 | 5937 | 1572 | 703 | 205 | 85 | 49 | 9 | 9 |  | 52174 | 52022
5 | 2014 | 31362 | 1319 | 825 | 224 | 752 | 61 | 7 | 10 |  |  | 34560 | 34482
6 | 2013 | 40888 | 3076 | 1155 | 737 | 742 | 52 | 69 | 15 | 10 | 2 | 46746 | 46598
7 | 2012 | 53452 | 3281 | 1016 | 522 | 478 | 28 | 11 | 15 | 3 | 1 | 58807 | 58749
8 | 2011 | 40341 | 2302 | 1271 | 678 | 893 | 18 | 11 | 3 |  | 1 | 45518 | 45485
9 | 2010 | 15455 | 1063 | 545 | 155 | 782 | 49 | 49 | 28 |  |  | 18126 | 18000
10 | 2009 | 8361 | 446 | 459 | 230 | 367 | 62 | 76 | 27 | 1 | 4 | 10033 | 9863
11 | 2008 | 12618 | 570 | 573 | 230 | 87 | 44 | 60 | 23 | 1 | 1 | 14207 | 14078
12 | 2007 | 9784 | 1446 | 382 | 235 | 172 | 37 | 17 | 24 | 6 | 1 | 12104 | 12019
13 | 2006 | 13119 | 1527 | 183 | 18 | 96 | 50 | 20 | 12 | 9 |  | 15034 | 14943
14 | 2005 | 11649 | 1404 | 479 | 262 | 50 | 58 | 40 | 17 | 2 |  | 13961 | 13844
15 | 2004 | 13256 | 1116 | 455 | 489 | 101 | 31 | 29 | 20 | 34 | 2 | 15533 | 15417
16 | 2003 | 12379 | 942 | 513 | 170 | 35 | 79 | 33 | 30 | 11 | 4 | 14196 | 14039
17 | 2002 | 7442 | 184 | 200 | 294 | 40 | 4 | 5 | 10 | 3 | 1 | 8183 | 8160
18 | 2001 | 10012 | 98 | 347 | 241 | 88 | 96 | 61 | 25 | 3 | 1 | 10972 | 10786
19 | 2000 | 3734 | 112 | 209 | 112 | 33 | 45 | 40 | 21 | 2 | 1 | 4309 | 4200
20 | 1999 | 1347 | 51 | 114 | 102 | 40 | 30 | 8 | 10 | 3 | 2 | 1707 | 1654
21 | 1998 | 1338 | 56 | 49 | 49 | 82 | 45 | 35 | 11 | 1 | 1 | 1667 | 1574
22 | 1997 | 739 | 13 | 19 | 31 | 25 | 6 | 14 | 4 |  | 1 | 852 | 827
23 | 1996 | 1293 | 9 | 33 | 58 | 32 | 8 | 9 | 2 |  | 1 | 1445 | 1425
24 | 1995 | 665 | 9 |  | 18 | 36 | 8 | 16 | 12 | 2 | 1 | 767 | 728
25 | 1994 | 279 | 8 | 8 | 12 | 10 | 6 | 3 | 3 |  |  | 329 | 317
26 | 1993 | 191 | 10 | 21 | 19 | 1 | 1 |  | 1 | 1 |  | 245 | 242
27 | 1992 | 170 | 2 | 3 | 12 | 3 |  | 2 | 4 | 2 | 1 | 199 | 190
28 | 1991 | 211 | 1 | 26 | 8 |  | 1 | 1 |  |  | 2 | 250 | 246
29 | 1990 | 101 |  | 15 | 9 | 2 | 1 | 5 |  |  |  | 133 | 127
30 | 1989 | 91 | 2 | 23 | 23 | 25 | 7 | 8 |  | 2 | 1 | 182 | 164
31 | 1988 | 45 | 3 | 19 | 17 | 3 | 1 | 3 | 5 |  |  | 96 | 87
32 | 1987 | 29 | 2 | 11 | 2 | 2 | 3 | 2 | 4 |  |  | 55 | 46
33 | 1986 | 79 | 1 | 21 | 31 | 5 | 4 | 9 | 2 | 1 |  | 153 | 137
34 | 1985 | 21 | 1 | 10 | 32 | 8 | 17 | 4 |  | 1 |  | 94 | 72
35 | 1984 | 13 |  | 8 | 33 | 2 | 17 | 8 | 4 | 1 |  | 86 | 56
36 | 1983 | 10 | 4 | 19 | 12 |  | 1 | 1 | 4 |  |  | 51 | 45
37 | 1982 | 5 |  | 5 | 10 | 4 | 3 |  | 2 |  |  | 29 | 24
38 | 1981 | 12 |  | 1 | 4 | 2 | 5 | 1 | 3 | 1 |  | 29 | 19
39 | 1980 | 4 | 1 | 2 |  | 2 | 2 | 2 | 3 |  |  | 16 | 9
40 | 1979 | 2 |  | 4 | 4 | 4 | 4 | 2 |  |  |  | 20 | 14
41 | 1978 |  |  | 1 | 3 |  |  | 1 | 1 |  | 2 | 8 | 4
42 | 1977 | 13 | [9 empty] | 13 | 13
43 | 1976 | 8 |  |  |  |  | 3 |  | 1 |  |  | 12 | 8
44 | 1975 | 14 | [5 empty] | 1 |  |  |  | 15 | 14
45 | 1974 | 6 |  |  |  |  | 2 |  | 1 |  |  | 9 | 6
46 | 1973 | 4 | [6 empty] | 1 |  | 1 | 6 | 4
47 | 1972 | 6 | [6 empty] | 1 |  |  | 7 | 6
48 | 1971 | 1 |  |  |  |  | 3 | 4 |  |  |  | 8 | 1
49 | 1970 | [5 empty] | 1 |  | 1 |  |  | 2 | 0
51 | 1969 | 2 | [9 empty] | 2 | 2
52 | 1968 | [5 empty] | 1 | 1 |  |  |  | 2 | 0
53 | 1967 | [5 empty] | 1 | 2 |  |  |  | 3 | 0
59 | 1966 | [7 empty] | 1 |  |  | 1 | 0
Current | Total: | 466958 | 34793 | 15071 | 8367 | 6096 | 1183 | 837 | 442 | 127 | 32 | 533906 | 531285
+ Est'd Growth | Total: | 31502.2232 | 2347.2279 | 922.4658 | 512.1273 | 278.4554 | 35.8461 | 25.3619 | 13.393 | 3.8482 | 0.96963 | 35641.9185 | 35562.4996 | Note 2
Grand | Total: | 498460.2232 | 37140.2279 | 15993.4658 | 8879.1273 | 6374.4554 | 1218.8461 | 862.3619 | 455.393 | 130.8482 | 32.9696 | 569547.9185 | 566847.4996
Note 1: | Unknown (DSP) Meters are no newer than 2013.
Note 2: | Includes Estimated Growth as forecast to occur from Oct. 2019 to Dec. 2022. THESE ARE CURRENTLY ASSUMED TO BE MECHANICAL METERS.

## 2. Meter Install Forecast-Est's
SAWS ConnectH2O Meter Installation Forecast & Projections | [9 empty] | 2019-11-11
THESE METER COUNTS ARE BASED ON BEST INFORMATION CURRENTLY AVAILABLE.
THESE NUMBERS ARE, HOWEVER, SUBJECT TO VARIATION AND CHANGE
[5 empty] | 2 mos. | 12 mos. | 12 mos. | 12 mos. | 10 mos. | Install/Retrofit #'s,
| 2017 | Oct. 2019 | Annual | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Assigned Installer:
Meter Size | Qty | Act. Qty* | Growth | Est'd Qty | Est'd Qty | Est'd Qty | Est'd Qty | Est'd Qty | Est'd Qty | Vendor | SAWS
|  |  | Assumed |  |  | note 3 | note 1, 2 | note 2 | note 2, 4 | note 3 | note 3
5/8" | 442963 | 466958 | 2.2% | 477231.076 | 487730.1597 | 498460.2232 | 509426.3481 | 520633.7278 | 532087.6698 | 498460.2232
3/4" | 38703 | 34793 | 2.2% | 35558.446 | 36340.7318 | 37140.2279 | 37957.3129 | 38792.3738 | 39645.806 | 37140.2279
1" | 14673 | 15071 | 2% | 15372.42 | 15679.8684 | 15993.4658 | 16313.3351 | 16639.6018 | 16972.3938 | 15993.4658
1-1/2" | 8041 | 8367 | 2% | 8534.34 | 8705.0268 | 8879.1273 | 9056.7099 | 9237.8441 | 9422.601 | 8879.1273
2" | 5702 | 6096 | 1.5% | 6187.44 | 6280.2516 | 6374.4554 | 6470.0722 | 6567.1233 | 6665.6301 | 6374.4554
3" | 1170 | 1183 | 1% | 1194.83 | 1206.7783 | 1218.8461 | 1231.0345 | 1243.3449 | 1255.7783 |  | 1218.8461
4" | 842 | 837 | 1% | 845.37 | 853.8237 | 862.3619 | 870.9856 | 879.6954 | 888.4924 |  | 862.3619
6" | 575 | 442 | 1% | 446.42 | 450.8842 | 455.393 | 459.947 | 464.5464 | 469.1919 |  | 455.393
8" |  | 127 | 1% | 128.27 | 129.5527 | 130.8482 | 132.1567 | 133.4783 | 134.8131 |  | 130.8482
10" |  | 32 | 1% | 32.32 | 32.6432 | 32.9696 | 33.2993 | 33.6323 | 33.9686 |  | 32.9696
Other | 0 | 0 | 2% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Totals | 512669 | 533906 |  | 545530.932 | 557409.7204 | 569547.9185 | 581951.2013 | 594625.3681 | 607576.345 | 566847.4996 | 2700.4189
| (WMP) | [8 empty] | 567000
|  |  |  | 2025: 2,500 for replacement of the other AMI Vendor whose technology was not selected | 2500
|  |  |  | 2025: Includes the extra 2,500 for replacement of the other AMI Vendor whose technology was not selected | 569500
* Data provided by Chrystal Alexander circa mid-October, 2019 | bar: 2020 to 2023
note 1: Assumes all new business installs will include "proper" new meter PLUS AMI Comms Module starting in 2023 and onwards
note 2: These are the estimated quantity of meters & new AMI communications modules required at end of each period.
note 3: These are the estimated quantity of meters that will exist & require replacement by EPI/SAWS, plus installation of
new AMI communications modules, at the end of 2022.
note 4: Represents the total number of existing meters, PLUS growth, that will occur through the end of a 48 Month FSWD Deployment Period.

## 3. Pilot+48 Mo FSWD Deploy Plan
Pilot + 48 Month Full System Wide Deployment | [7 empty] | Appendix 6 - SAWS Connect H2O AMI Water Deployment – Initial Plan
2019-11-11 |  |  |  | WATER:
|  |  | Total Water: | 569547.9185 | (Includes Growth thru 2022)
|  |  | Vendor Qty: | 566847.4996 | Less than 3"; also add 2500 extra
|  |  | SAWS Qty: | 2700.4189 | 3" or greater
EPI Vendor to fill in these cells
[5 empty] | VENDOR - Resid. (5/8" up to and including 2") |  |  |  |  | Option - Vendor in lieu of SAWS - Comm. (3" and greater) |  |  |  |  | All Water Meters
| Mo-Yr | AMI-EPI Contract Mo. # | Program Phase Mo. # | Deploy- ment Mo. # | # installers | Avg meters per day per installer | Avg. meters per week - all persons | Avg. meters per month - all persons | Cumulative Meters installed | # installers | Avg meters per day per installer | Avg. meters per week - all persons | Avg. meters per month - all persons | Cumulative Meters installed | # installers | Avg meters per day per installer | Avg. meters per week - all persons | Avg. meters per month - all persons | Cumulative Meters installed | By Year, Cum. Meters installed
AMI/MDMS | 2020-06-01 | 1 | 1 | 0 |  |  | - | 0 | 0 |  |  | - | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
Ph 2, Pilot, TA 1 | 2020-07-01 | 2 | 2 | 1 | Note 1 |  | - | 100 | 100 |  |  | - | 0 | 0 | #VALUE! | 0 | #VALUE! | 100 | 100 | 100
Ph 2, Pilot, TA 1 & 2 | 2020-08-01 | 3 | 3 | 2 | Note 1 |  | - | 633.3333 | 733.3333 | Note 2 |  | - | 5 | 5 | #VALUE! | 0 | #VALUE! | 638.3333 | 738.3333 | 738.3333
Ph 2 Pilot, TA 2 & 3 | 2020-09-01 | 4 | 4 | 3 | Note 1 |  | - | 2766.6667 | 3500 | Note 2 |  | - | 5 | 10 | #VALUE! | 0 | #VALUE! | 2771.6667 | 3510 | 3510
Ph 2, Pilot, TA 3 | 2020-10-01 | 5 | 5 | 4 | Note 1 |  | - | 1500 | 5000 | Note 2 |  | - | 5 | 15 | #VALUE! | 0 | #VALUE! | 1505 | 5015 | 5015
| 2020-11-01 | 6 | 6 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 5015
| 2020-12-01 | 7 | 7 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 5015 | 0.8764% | 2020
AMI/MDMS | 2021-01-01 | 8 | 8 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
Phase 2, Pilot | 2021-02-01 | 9 | 9 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
(Cont'd) | 2021-03-01 | 10 | 10 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
| 2021-04-01 | 11 | 11 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
| 2021-05-01 | 12 | 12 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
AMI/MDMS | 2021-06-01 | 13 | 1 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
Phase 3 - FSWD | 2021-07-01 | 14 | 2 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
| 2021-08-01 | 15 | 3 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
| 2021-09-01 | 16 | 4 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
| 2021-10-01 | 17 | 5 |  |  |  | 0 | 0 | 5000 |  |  | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 5015 | 0
| 2021-11-01 | 18 | 6 | 1 |  |  | 25 | 100 | 5100 |  |  | 5 | 20 | 35 | 0 | 0 | 30 | 120 | 5135 | 120
| 2021-12-01 | 19 | 7 | 2 |  |  | 250 | 1000 | 6100 |  |  | 8.75 | 35 | 70 | 0 | 0 | 258.75 | 1035 | 6170 | 1155 | 0.2018% | 2021
AMI/MDMS | 2022-01-01 | 20 | 8 | 3 |  |  | 625 | 2500 | 8600 |  |  | 12.5 | 50 | 120 | 0 | 0 | 637.5 | 2550 | 8720 | 2550
Phase 3 - FSWD | 2022-02-01 | 21 | 9 | 4 |  |  | 1000 | 4000 | 12600 |  |  | 15 | 60 | 180 | 0 | 0 | 1015 | 4060 | 12780 | 6610
(cont'd) | 2022-03-01 | 22 | 10 | 5 |  |  | 1625 | 6500 | 19100 |  |  | 15 | 60 | 240 | 0 | 0 | 1640 | 6560 | 19340 | 13170
| 2022-04-01 | 23 | 11 | 6 |  |  | 2250 | 9000 | 28100 |  |  | 15 | 60 | 300 | 0 | 0 | 2265 | 9060 | 28400 | 22230
| 2022-05-01 | 24 | 12 | 7 |  |  | 2875 | 11500 | 39600 |  |  | 15 | 60 | 360 | 0 | 0 | 2890 | 11560 | 39960 | 33790
| 2022-06-01 | 25 | 13 | 8 |  |  | 3393.75 | 13575 | 53175 |  |  | 15 | 60 | 420 | 0 | 0 | 3408.75 | 13635 | 53595 | 47425
| 2022-07-01 | 26 | 14 | 9 |  |  | 3393.75 | 13575 | 66750 |  |  | 15 | 60 | 480 | 0 | 0 | 3408.75 | 13635 | 67230 | 61060
| 2022-08-01 | 27 | 15 | 10 |  |  | 3393.75 | 13575 | 80325 |  |  | 15 | 60 | 540 | 0 | 0 | 3408.75 | 13635 | 80865 | 74695
| 2022-09-01 | 28 | 16 | 11 |  |  | 3393.75 | 13575 | 93900 |  |  | 15 | 60 | 600 | 0 | 0 | 3408.75 | 13635 | 94500 | 88330
| 2022-10-01 | 29 | 17 | 12 |  |  | 3393.75 | 13575 | 107475 |  |  | 15 | 60 | 660 | 0 | 0 | 3408.75 | 13635 | 108135 | 101965
| 2022-11-01 | 30 | 18 | 13 |  |  | 3393.75 | 13575 | 121050 |  |  | 15 | 60 | 720 | 0 | 0 | 3408.75 | 13635 | 121770 | 115600
| 2022-12-01 | 31 | 19 | 14 |  |  | 3393.75 | 13575 | 134625 |  |  | 15 | 60 | 780 | 0 | 0 | 3408.75 | 13635 | 135405 | 129235 | 22.58% | 2022
AMI/MDMS | 2023-01-01 | 32 | 20 | 15 |  |  | 3393.75 | 13575 | 148200 |  |  | 15 | 60 | 840 | 0 | 0 | 3408.75 | 13635 | 149040 | 13635
Phase 3 - FSWD | 2023-02-01 | 33 | 21 | 16 |  |  | 3393.75 | 13575 | 161775 |  |  | 15 | 60 | 900 | 0 | 0 | 3408.75 | 13635 | 162675 | 27270
(cont'd) | 2023-03-01 | 34 | 22 | 17 |  |  | 3393.75 | 13575 | 175350 |  |  | 15 | 60 | 960 | 0 | 0 | 3408.75 | 13635 | 176310 | 40905
| 2023-04-01 | 35 | 23 | 18 |  |  | 3393.75 | 13575 | 188925 |  |  | 15 | 60 | 1020 | 0 | 0 | 3408.75 | 13635 | 189945 | 54540
| 2023-05-01 | 36 | 24 | 19 |  |  | 3393.75 | 13575 | 202500 |  |  | 15 | 60 | 1080 | 0 | 0 | 3408.75 | 13635 | 203580 | 68175
| 2023-06-01 | 37 | 25 | 20 |  |  | 3393.75 | 13575 | 216075 |  |  | 15 | 60 | 1140 | 0 | 0 | 3408.75 | 13635 | 217215 | 81810
| 2023-07-01 | 38 | 26 | 21 |  |  | 3393.75 | 13575 | 229650 |  |  | 15 | 60 | 1200 | 0 | 0 | 3408.75 | 13635 | 230850 | 95445
| 2023-08-01 | 39 | 27 | 22 |  |  | 3393.75 | 13575 | 243225 |  |  | 15 | 60 | 1260 | 0 | 0 | 3408.75 | 13635 | 244485 | 109080
| 2023-09-01 | 40 | 28 | 23 |  |  | 3393.75 | 13575 | 256800 |  |  | 15 | 60 | 1320 | 0 | 0 | 3408.75 | 13635 | 258120 | 122715
| 2023-10-01 | 41 | 29 | 24 |  |  | 3393.75 | 13575 | 270375 |  |  | 15 | 60 | 1380 | 0 | 0 | 3408.75 | 13635 | 271755 | 136350
| 2023-11-01 | 42 | 30 | 25 |  |  | 3393.75 | 13575 | 283950 |  |  | 15 | 60 | 1440 | 0 | 0 | 3408.75 | 13635 | 285390 | 149985
| 2023-12-01 | 43 | 31 | 26 |  |  | 3393.75 | 13575 | 297525 |  |  | 15 | 60 | 1500 | 0 | 0 | 3408.75 | 13635 | 299025 | 163620 | 28.59% | 2023
AMI/MDMS | 2024-01-01 | 44 | 32 | 27 |  |  | 3393.75 | 13575 | 311100 |  |  | 15 | 60 | 1560 | 0 | 0 | 3408.75 | 13635 | 312660 | 13635
Phase 3 - FSWD | 2024-02-01 | 45 | 33 | 28 |  |  | 3393.75 | 13575 | 324675 |  |  | 15 | 60 | 1620 | 0 | 0 | 3408.75 | 13635 | 326295 | 27270
(cont'd) | 2024-03-01 | 46 | 34 | 29 |  |  | 3393.75 | 13575 | 338250 |  |  | 15 | 60 | 1680 | 0 | 0 | 3408.75 | 13635 | 339930 | 40905
| 2024-04-01 | 47 | 35 | 30 |  |  | 3393.75 | 13575 | 351825 |  |  | 15 | 60 | 1740 | 0 | 0 | 3408.75 | 13635 | 353565 | 54540
| 2024-05-01 | 48 | 36 | 31 |  |  | 3393.75 | 13575 | 365400 |  |  | 15 | 60 | 1800 | 0 | 0 | 3408.75 | 13635 | 367200 | 68175
| 2024-06-01 | 49 | 37 | 32 |  |  | 3393.75 | 13575 | 378975 |  |  | 15 | 60 | 1860 | 0 | 0 | 3408.75 | 13635 | 380835 | 81810
| 2024-07-01 | 50 | 38 | 33 |  |  | 3393.75 | 13575 | 392550 |  |  | 15 | 60 | 1920 | 0 | 0 | 3408.75 | 13635 | 394470 | 95445
| 2024-08-01 | 51 | 39 | 34 |  |  | 3393.75 | 13575 | 406125 |  |  | 15 | 60 | 1980 | 0 | 0 | 3408.75 | 13635 | 408105 | 109080
| 2024-09-01 | 52 | 40 | 35 |  |  | 3393.75 | 13575 | 419700 |  |  | 15 | 60 | 2040 | 0 | 0 | 3408.75 | 13635 | 421740 | 122715
| 2024-10-01 | 53 | 41 | 36 |  |  | 3393.75 | 13575 | 433275 |  |  | 15 | 60 | 2100 | 0 | 0 | 3408.75 | 13635 | 435375 | 136350
| 2024-11-01 | 54 | 42 | 37 |  |  | 3393.75 | 13575 | 446850 |  |  | 15 | 60 | 2160 | 0 | 0 | 3408.75 | 13635 | 449010 | 149985
| 2024-12-01 | 55 | 43 | 38 |  |  | 3393.75 | 13575 | 460425 |  |  | 15 | 60 | 2220 | 0 | 0 | 3408.75 | 13635 | 462645 | 163620 | 28.59% | 2024
AMI/MDMS | 2025-01-01 | 56 | 44 | 39 |  |  | 3393.75 | 13575 | 474000 |  |  | 15 | 60 | 2280 | 0 | 0 | 3408.75 | 13635 | 476280 | 13635
Phase 3 - FSWD | 2025-02-01 | 57 | 45 | 40 |  |  | 3393.75 | 13575 | 487575 |  |  | 15 | 60 | 2340 | 0 | 0 | 3408.75 | 13635 | 489915 | 27270
(cont'd) | 2025-03-01 | 58 | 46 | 41 |  |  | 3393.75 | 13575 | 501150 |  |  | 15 | 60 | 2400 | 0 | 0 | 3408.75 | 13635 | 503550 | 40905
| 2025-04-01 | 59 | 47 | 42 |  |  | 3393.75 | 13575 | 514725 |  |  | 15 | 60 | 2460 | 0 | 0 | 3408.75 | 13635 | 517185 | 54540
| 2025-05-01 | 60 | 48 | 43 |  |  | 3393.75 | 13575 | 528300 |  |  | 15 | 60 | 2520 | 0 | 0 | 3408.75 | 13635 | 530820 | 68175
| 2025-06-01 | 61 | 49 | 44 |  |  | 3393.75 | 13575 | 541875 |  |  | 15 | 60 | 2580 | 0 | 0 | 3408.75 | 13635 | 544455 | 81810
| 2025-07-01 | 62 | 50 | 45 |  |  | 3393.75 | 13575 | 555450 |  |  | 15 | 60 | 2640 | 0 | 0 | 3408.75 | 13635 | 558090 | 95445
| 2025-08-01 | 63 | 51 | 46 |  |  | 1825 | 7300 | 562750 |  |  | 10 | 40 | 2680 | 0 | 0 | 1835 | 7340 | 565430 | 102785
| 2025-09-01 | 64 | 52 | 47 |  |  | 1125 | 4500 | 567250 |  |  | 7.5 | 30 | 2710 | 0 | 0 | 1132.5 | 4530 | 569960 | 107315
| 2025-10-01 | 65 | 53 | 48 |  |  | 562.5 | 2250 | 569500 |  |  | 5 | 20 | 2730 | 0 | 0 | 567.5 | 2270 | 572230 | 109585
| 2025-11-01 | 66 | 54 |  |  |  | 0 | 0 | 569500 |  |  | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 572230 | 109585
| 2025-12-01 | 67 | 55 |  |  |  | 0 | 0 | 569500 |  |  | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 572230 | 109585 | 19.15% | 2025
AMI/MDMS | 2026-01-01 | 68 | 56 |  |  |  | 0 | 0 | 569500 |  |  | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 572230 | 0
Phase 3 - FSWD | 2026-02-01 | 69 | 57 |  |  |  | 0 | 0 | 569500 |  |  | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 572230 | 0
(cont'd) | 2026-03-01 | 70 | 58 |  |  |  | 0 | 0 | 569500 |  |  | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 572230 | 0
| 2026-04-01 | 71 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-05-01 | 72 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-06-01 | 73 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-07-01 | 74 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-08-01 | 75 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-09-01 | 76 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-10-01 | 77 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-11-01 | 78 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
| 2026-12-01 | 79 | [6 empty] | 569500 |  |  |  |  | 2730 |  |  |  |  | 572230
[5 empty] | Note 1: SAWS has requested Option for Pilot Residential Meters | [5 empty] | Note 2: SAWS to Install in Pilot. | [8 empty] | 572230
to be Installed by EPI Vendor (See Exhibit A - EPI Pricing Workbook, for details)
Note on K74: MARK: Includes replacement of 2500 of the Pilot Meters from other AMI Vendor.
Note on W74: MARK: Includes replacement of 2500 of the Pilot Meters from other AMI Vendor.

## 4. Pilot + 48 Mo. FSWD Graphs
Appendix 6 - SAWS ConnectH2O AMI Water Deployment – Initial Plan