## Respondent Info & Instructions
Respondent Information & Instructions, EPI Pricing Workbook
Scenario 3: End Date 6.30.27
Items | Respondent Requested Information | Respondent Data
| Throughout the Workbook, Cells highlighted in "Yellow" require Respondent's input: | As denoted
1 | Name of Respondent's company here:
2 | Date of Respindent's submittal here:
Notes to Respondent:
3 | GENERAL NOTE: The Offer is advised that it shall not modify or alter any cells or formulas in this workbook. These cells and formulas are carefully and widely linked throughout the various worksheets so as to calculate the cost of various options and combinations as specified herein by SAWS.
4 | The Respondent must start by entering its inputs to Tab "2 FSWD Scenario X, End XX.XX.XX" of this workbook to establish the annual quantity of meters, by size, that Respondent will install. The data for Tab "2 FSWD Scenario X, End XX.XX.XX" is to be cut 'n pasted by Respondent from its data entered in "Appendix 6 - Water Deployment Plan" for the respecitve Scenario 1 /2 / 3. Entry of its cut 'n paste data on this Tab results in the auto-populating of the meter quantities by year and size on Tab "Meter Install Forecast-Est's". This resulting data then drives and auto-populates the quantities on the respective Tabs 2A, 3 & 4 of this file.
5 | SAWS intends to have Respondent install Static Meters. Mandatory responses are required for meter sizes 5/8" to 2", in the quantities as shown on worksheet "2A Static (SM)+Comms Mod Install". The quantities and timeframes for installation are SAWS' best estimate at this time. Some small deviations in quantities and timeframes may occur.
6 | SAWS has requested responses for meter sizes 3" to 10", in the quantities as shown on worksheet "2A Static (SM)+Comms Mod Install". SAWS' reserves the option to award the installation of these to the Respondent.
7 | For Tabs 2A, 3, and most of 4: The quantities for the respective devices are automatically populated into these Tabs. The Respondent shall provide the indicated Unit Price information in Yellow cells. SAWS will pay the Respondent for the number of devices times the Respondent's Unit Price for that respective time period.
8 | Tab 4, Lines 63:68: These lines provide the opportunity for the Respondent to add any other pricing it feels should be considered by SAWS. If provided, Respondent is required to add its own estimated quantities, as well as its proposed Unit Prices, for these items.
9 | For Tab 5, Respondent is requested to provide its key Assumptions as specified therein.
10 | Tab 1A: Provides an automatic rollup and summary of the annual, escalated, prices that result from Respondent's entries of unit prices for various items from Tabs 2A, 3 & 4.
11 | Tab 1B: Provides a high level rolloup of the total, escalated costs for small (5/8 - 2" meters) and large (3" - 10" meters) installation costs.

## 1A Cost Opts-Summary, Esclt'd
Tab 1A, Summary Pricing, Static Meters
Scenario 3: End Date 6.30.27
Respondent: |  | 0
Date |  | 0 | NO EPI VENDOR DATA ENTRY TO BE PERFORMED ON THIS SHEET. |  |  |  |  | Please refer to Appendix 6 - SAWS AMI Water Deployment Plan,
for Details re. the Meter Population and Services, Below.
| Summary of Escalated $Costs (Calculated) |  |  |  | Details of Escalated Costs (Calculated)
Item | Totals | $Avg. Cost/ Meter | # Meters | Sizes | 2. 100% Static | 3. Other Equipment | 4. Services & Support | Meter Info | / Size | 5/8" | 3/4" | 1" | 1.5" | 2" | 3" | 4" | 6" | 8" | 10" | Current Total | 2" and Less | 3" - 10"
| Static Meter Pricing: |  | FSWD |  |  |  |  | Static Meters: | REPLACE ALL METERS WITH NEW STATIC MTRS & INSTALL AMI COMMUNICATIONS MODULE. | [13 empty] | OPTION 4
Scenario 3: End Date 6.30.27
1S | #DIV/0! | #DIV/0! | 0 | 5/8" - 2" | 0 | 0 | #DIV/0! | 5/8" - 2" | Totals: | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | Replace ALL w/Static Mtr + Install AMI Comms Module
1L | 0 | #DIV/0! | 0 | 3" - 10" | 0 |  |  | 3" - 10" | Totals: | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1Total | #DIV/0! | #DIV/0! | 0 | (All) |  |  |  | Grand | Total: | [10 empty] | 0

## 1B Cost Opts-Detailed, Esclt'd
Tab 1B, Estimated, Escalated Costs, Static Meters
Scenario 3: End Date 6.30.27 |  | 0
Estimated Contract Costs |  | 0
NO EPI VENDOR DATA ENTRY TO BE PERFORMED ON THIS SHEET.
Scenario 3: End Date 6.30.27 |  | Replace 100% w/ Static Mtrs + Inst/Comms | ALL | ALL | ALL | ALL | ALL |  | ALL
| Results, Deployment totals 2023 - 2027 | Total Cost | 2023 | 2024 | 2025 | 2026 | 2027 |  | Total
Results:
| 2 Install Static Residential Meters (5/8" - 2") | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | #DIV/0!
| 2 Vendor Install Static C&I Meters (3" - 10") | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | #DIV/0!
| 3 Install And/Or Replace Other Equipment | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | #DIV/0!
| 3.1 OE1: Replacement of Curb Stop Valves | 0 | 0 | 0 | 0 | 0 | 0
| 3.2 OE2: Installation of Meter Boxes | 0 | 0 | 0 | 0 | 0 | 0
| 3.3 OE3: Installation or Replacement of Yokes | 0 | 0 | 0 | 0 | 0 | 0
| 3.4 OE4: Re-set or Re-Level Meter Boxes | 0 | 0 | 0 | 0 | 0 | 0
| 3.5 OE5: Installation of Meter Connections | 0 | 0 | 0 | 0 | 0 | 0
| 4 Other Services & Support | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 4.1 Work Order Management System (WOMS) | 0 | 0 | 0 | 0 | 0 | 0
| 4.2 Call Center Services | 0 | 0 | 0 | 0 | 0 | 0
| 4.3 Warehouse/Cross-Dock Facilities | 0 | 0 | 0 | 0 | 0 | 0
| 4.4 Project Management Services | 0 | 0 | 0 | 0 | 0 | 0
| 4.5 Hourly Wages for Extra Work | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 4.6 Payment & Performance Bonds | 0 | 0 | 0 | 0 | 0 | 0
| 4.7 Other SAWS Pricing | 0 | 0 | 0 | 0 | 0 | 0
| 4.8 Other EPI Pricing | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| # Meters | 0
| Average Cost per Meter | #DIV/0!

## 2A Static (SM)+Comms Mod Instal
Tab 2A, Static Meter (SM) + Comms Module Installation Services
Scenario 3: End Date 6.30.27
Respondent: |  | 0
Date |  | 0
Coding to be used for table
Yellow Cell inputs |  | Respondent's Information
Water Installation: | [10 empty] | Full System Wide Deployment | [6 empty] | FSWD: 5/8" - 2" Meters |  |  |  | FSWD: Annual Cash Flow
2A. Installation of new static Water Meter (meter + encoder/register) PLUS Communications Modules | Static Meter (SM) Pricing Item No. | Meter Size | Meter Manuf. | Meter Type | Estimated Install Qty by EPI (2023) | Estimated Install Qty by EPI (2024) | Estimated Install Qty by EPI (2025) | Estimated Install Qty by EPI (2026) | Estimated Install Qty by EPI (2027) | Total Estimated Install Qty by EPI | EPI's Installation Unit Price (2023) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2024) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2025) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2026) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2027) (Notes 1, 2, 3, 4) | (Resulting) EPI's Extended Cost | Descr. | Total Qty | (Resulting) EPI's Extended Cost | 2023 | 2024 | 2025 | 2026 | 2027
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM1J | 5/8" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 5/8" Static Meter + 500W | 0 | 0 | 0
| SM1K | 5/8" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM1L | 5/8" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM1M | 5/8" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM1N | 5/8" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM2H | 3/4" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 3/4" Static Meter + 500W | 0 | 0 | 0
| SM2J | 3/4" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM2L | 3/4" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM2M | 3/4" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM2N | 3/4" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM3J | 1" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 1" Static Meter + 500W | 0 | 0 | 0
| SM3K | 1" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM3L | 1" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM3M | 1" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM3N | 1" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM4J | 1 1/2" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 1.5" Static Meter + 500W | 0 | 0 | 0
| SM4K | 1 1/2" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM4L | 1 1/2" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM4M | 1 1/2" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM4N | 1 1/2" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM5H | 2" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 2" Static Meter + 500W | 0 | 0 | 0
| SM5J | 2" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM5L | 2" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM5M | 2" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM5N | 2" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Total, Meters 5/8" to 2": |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Large Meter Work (3" and Larger) (Note 5) | [17 empty] | FSWD: 3" - 10" Meters
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM6D | 3" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 3" Static Meter + 500W | 0 | 0 | 0
| SM6E | 3" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM6F | 3" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM6G | 3" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM6H | 3" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM7D | 4" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 4" Static Meter + 500W | 0 | 0 | 0
| SM7E | 4" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM7F | 4" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM7G | 4" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM7H | 4" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM8D | 6" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 6" Static Meter + 500W | 0 | 0 | 0
| SM8E | 6" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM8F | 6" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM8G | 6" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM8H | 6" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Satic Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM9D | 8" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 8" Static Meter + 500W | 0 | 0 | 0
| SM9E | 8" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM9F | 8" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM9G | 8" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM9H | 8" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Static Meter Installation (Meter + Encoder/Register) PLUS Water Communications Module Installation | SM10D | 10" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install 10" Static Meter + 500W | 0 | 0 | 0
| SM10E | 10" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0
| SM10F | 10" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| SM10G | 10" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [6 empty] | 0
| SM10H | 10" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | TRUE
Total, Meters 3" to 10": |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Note 1: EPI's Installation Unit Pricing shall be fully loaded and include all field supervision & field quality audit labor; field installation workforce labor; photographs, fleet, tools and equipment, uniforms, safety equipment, et al; as specified in RFCSP.
Note 2: EPI's Work Order Management shall be fully loaded and include the work order management system & handheld field devices, inclusive of all support as is required to perform daily work planning, issuing, data upload/download activities, et al. as specified in RFCSP.
Note 3: EPI's Cross Dock Unit Pricing shall be fully loaded and include all cross dock labor and support as is required to perform daily staging and issuing meters and modules; receive used meters & modules; implement the scrapping process, and handle materials flows to/between the EPI and SAWS, as specified in RFCSP.
Note 4: Furnish all materials except SAWS supplied equipment, as specified in RFCSP.
Note 5: For meters sized 3" through 10", EPI is requested to provide a quote to perform installation of these meters. Installation costs shall include all trucks, equipment and lifting machinery as required for EPI to complete this work. SAWS reserves the right to assign these to EPI for installation at SAWS' discretion.

## 3 Other Equip (OE) Install
Tab 3, Other Equipment (OE) Installation Services
Scenario 3: End Date 6.30.27
Respondent: |  | 0
Date |  | 0
Coding to be used for table
Yellow Cell inputs |  | Respondent's Information
Water Installation: | [10 empty] | Full System Wide Deployment | [6 empty] | FSWD: Other Equipment |  |  |  |  | FSWD: Annual Cash Flow
3. Installation and/or Replacement of Other Equipment & Devices | Other Equipment (OE) Pricing Item No. | Meter Size | Meter Manuf. | Meter Type | Estimated Install Qty by EPI (2023) | Estimated Install Qty by EPI (2024) | Estimated Install Qty by EPI (2025) | Estimated Install Qty by EPI (2026) | Estimated Install Qty by EPI (2027) | Total Estimated Install Qty by EPI | EPI's Installation Unit Price (2023) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2024) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2025) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2026) (Notes 1, 2, 3, 4) | EPI's Installation Unit Price (2027) (Notes 1, 2, 3, 4) | (Resulting) EPI's Extended Cost | Descr. | Total Qty | % | (Resulting) EPI's Extended Cost | 2023 | 2024 | 2025 | 2025 | 2027
3.1 Replacement of Curb Stop Valves (5/8" - 1") | OE1K | 5/8" to 1" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Replace Curb Stop Valves, 5/8 - 1" | 0 | 3.5% | 0 | 0
| OE1L | 5/8" to 1" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| OE1M | 5/8" to 1" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [6 empty] | 0
| OE1N | 5/8" to 1" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0
| OE1O | 5/8" to 1" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 | TRUE
3.1 Replacement of Curb Stop Valves (1.5" - 2") | OE1P | 1-1/2" to 2" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Replace Curb Stop Valves, 1.5 - 2" | 0 | 10% | 0 | 0
| OE1Q | 1-1/2" to 2" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| OE1R | 1-1/2" to 2" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [6 empty] | 0
| OE1S | 1-1/2" to 2" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0
| OE1T | 1-1/2" to 2" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 | TRUE
3.2 Installation or Replacement of Meter Boxes | OE2G | 5/8" to 2" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install or Replace Meter Boxes, 5/8 - 2" | 0 | 5.29% | 0 | 0
| OE2H | 5/8" to 2" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| OE2J | 5/8" to 2" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [6 empty] | 0
| OE2K | 5/8" to 2" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0
| OE2L | 5/8" to 2" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 | TRUE
3.3 Installation or Replacement of Yokes | OE3E | 5/8" to 2" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Install or Replace Yokes, 5/8 - 2" | 0 | 1% | 0 | 0
| OE3F | 5/8" to 2" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| OE3G | 5/8" to 2" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [6 empty] | 0
| OE3H | 5/8" to 2" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0
| OE3J | 5/8" to 2" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 | TRUE
3.4 Re-Set or Re-Level Meter Boxes | OE4F | 5/8" to 2" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Re-Set or Re-Level Meter Boxes, 5/8 - 2" | 0 | 15% | 0 | 0
| OE4G | 5/8" to 2" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| OE4H | 5/8" to 2" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [6 empty] | 0
| OE4J | 5/8" to 2" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0
| OE4K | 5/8" to 2" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 | TRUE
3.5 Installation of Meter Connections | OE5A | 5/8" to 1" | All | All | 0 |  |  |  |  | 0 | [5 empty] | 0 | Installation of Meter Connections, 5/8" - 1" | 0 | 6% | 0 | 0
| OE5B | 5/8" to 1" | All | All |  | 0 |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 0
| OE5C | 5/8" to 1" | All | All |  |  | 0 |  |  | 0 | [5 empty] | 0 | [6 empty] | 0
| OE5D | 5/8" to 1" | All | All |  |  |  | 0 |  | 0 | [5 empty] | 0 | [7 empty] | 0
| OE5E | 5/8" to 1" | All | All |  |  |  |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 | TRUE
Total: | [15 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Note 1: EPI's Installation Unit Pricing shall be fully loaded and include all field supervision & field quality audit labor; field installation workforce labor; photographs, fleet, tools and equipment, uniforms, safety equipment, et al; as specified in RFCSP.
Note 2: EPI's Work Order Management shall be fully loaded and include the work order management system & handheld field devices, inclusive of all support as is required to perform daily work planning, issuing, data upload/download activities, et al. as specified in RFCSP.
Note 3: EPI's Cross Dock Unit Pricing shall be fully loaded and include all cross dock labor and support as is required to perform daily staging and issuing meters and modules; receive used meters & modules; implement the scrapping process, and handle materials flows to/between the EPI and SAWS, as specified in RFCSP.
Note 4: Furnish all materials except SAWS supplied equipment, as specified in RFCSP.

## 4 Services & Support (SS) Prcng
Tab 4: Services & Support (SS)
Scenario 3: End Date 6.30.27
Respondent's: | 0
Date | 0
Coding to be used for table
Yellow Cell inputs | Respondent's Information
| Water Installation: | [10 empty] | Full System Wide Deployment | [5 empty] | FSWD: Services & Support |  |  |  |  | FSWD: Annual Cash Flow
4. Other Services and Support | Other Services (OS) Pricing Item No. | Unit of Measure | Cost Desc. | Estimated Install Qty by EPI (2023) | Estimated Install Qty by EPI (2024) | Estimated Install Qty by EPI (2025) | Estimated Install Qty by EPI (2026) | Estimated Install Qty by EPI (2027) | Total Estimated Install Qty by EPI | Included in Tabs 2 or 3? (Yes/No) (Note 6) | EPI's Unit Price (2023) | EPI's Unit Price (2024) | EPI's Unit Price (2025) | EPI's Unit Price (2026) | EPI's Unit Price (2027) | (Resulting) EPI's Extended Cost | Descr. | Total Qty | % | (Resulting) EPI's Extended Cost | 2023 | 2024 | 2025 | 2026 | 2027
4.1 Work Order Management System (WOMS):
Develop Work Flows; Stand Up, Integrate & Test (Note 8) | SS1D | 1-time fee | 1-time | 0 |  |  |  |  | 0 | na | 0 |  |  |  |  | 0 | WOMS Startup, 1-Time | 0 | n/a | 0 | 0 |  |  |  |  | TRUE
Operate & Maintain WOMS, Full System Wide Deployment (FSWD) (Note 8, 9) | SS1E | months | FSWD | 3 |  |  |  |  | 3 | [6 empty] | 0 | WOMS Operate, Monthly Recurring | 45 | n/a | 0 | 0
| SS1F | months |  |  | 12 |  |  |  | 12 | [6 empty] | 0 | [5 empty] | 0
| SS1G | months |  |  |  | 12 |  |  | 12 | [6 empty] | 0 | [6 empty] | 0
| SS1H | months |  |  |  |  | 12 |  | 12 | [6 empty] | 0 | [7 empty] | 0
| SS1J | months | [5 empty] | 6 | 6 | [6 empty] | 0 | [8 empty] | 0 | TRUE
4.2 Call Center:
Develop Processes & Scripts; Stand Up, Integrate & Test (Note 8) | SS2D | 1-time fee | 1-time | 0 |  |  |  |  | 0 | na | 0 |  |  |  |  | 0 | Call Center Startup, 1-Time | 0 | n/a | 0 | 0 |  |  |  |  | TRUE
Operate Call Center, FSWD (Note 8, 9) | SS2E | months | FSWD | 3 |  |  |  |  | 3 | [6 empty] | 0 | Call Center Operate, Monthly Recurring | 45 | n/a | 0 | 0
| SS2F | months |  |  | 12 |  |  |  | 12 | [6 empty] | 0 | [5 empty] | 0
| SS2G | months |  |  |  | 12 |  |  | 12 | [6 empty] | 0 | [6 empty] | 0
| SS2H | months |  |  |  |  | 12 |  | 12 | [6 empty] | 0 | [7 empty] | 0
| SS2J | months | [5 empty] | 6 | 6 | [6 empty] | 0 | [8 empty] | 0 | TRUE
4.3 Warehouse/X-Dock Facility Charge:
Mobilize & Stand Up (Note 8) | SS3C | 1-time fee | 1-time | 0 |  |  |  |  | 0 | na | 0 |  |  |  |  | 0 | Warehouse Mobilize, 1-Time | 0 | n/a | 0 | 0 |  |  |  |  | TRUE
Warehouse/X-Dock Facility Monthly Lease, FSWD (Note 9) | SS3D | months | FSWD | 3 |  |  |  |  | 3 | [6 empty] | 0 | Warehouse/ Cross Dock Lease, Monthly Recurring | 45 | n/a | 0 | 0
| SS3E | months |  |  | 12 |  |  |  | 12 | [6 empty] | 0 | [5 empty] | 0
| SS3F | months |  |  |  | 12 |  |  | 12 | [6 empty] | 0 | [6 empty] | 0
| SS3G | months |  |  |  |  | 12 |  | 12 | [6 empty] | 0 | [7 empty] | 0
| SS3H | months | [5 empty] | 6 | 6 | [6 empty] | 0 | [8 empty] | 0 | TRUE
Operate Warehouse/Cross-Dock, FSWD (Note 8, 9) | SS3H | months | FSWD | 3 |  |  |  |  | 3 | [6 empty] | 0 | Warehouse/ Cross Dock Operate, Monthly Recurring | 45 | n/a | 0 | 0
| SS3J | months |  |  | 12 |  |  |  | 12 | [6 empty] | 0 | [5 empty] | 0
| SS3K | months |  |  |  | 12 |  |  | 12 | [6 empty] | 0 | [6 empty] | 0
| SS3L | months |  |  |  |  | 12 |  | 12 | [6 empty] | 0 | [7 empty] | 0
| SS3M | months | [5 empty] | 6 | 6 | [6 empty] | 0 | [8 empty] | 0 | TRUE
4.4 Project Management Services:
Mobilize (Note 8) | SS4D | 1-time fee | 1-time | 0 |  |  |  |  | 0 | na | 0 |  |  |  |  | 0 | Project Mgmt Mobilize, 1-Time | 0 | n/a | 0 | 0 |  |  |  |  | TRUE
Project Management Services, FSWD (Note 8, 9) | SS4E | months | FSWD | 3 |  |  |  |  | 3 | [6 empty] | 0 | Project Management, Monthly Recurring | 45 | n/a | 0 | 0
| SS4F | months |  |  | 12 |  |  |  | 12 | [6 empty] | 0 | [5 empty] | 0
| SS4G | months |  |  |  | 12 |  |  | 12 | [6 empty] | 0 | [6 empty] | 0
| SS4H | months |  |  |  |  | 12 |  | 12 | [6 empty] | 0 | [7 empty] | 0
| SS4J | months | [5 empty] | 6 | 6 | [6 empty] | 0 | [8 empty] | 0 | TRUE
4.5 Hourly Wage Rates for Extra Work:
Water Meter Technician 1 (Sizes: 5/8" to 2") (Note 7) | SS5D | $/hour | Fully Loaded Hourly Wage Rate | #DIV/0! |  |  |  |  | #DIV/0! | [6 empty] | #DIV/0! | Water Meter Technician, Extra Work | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| SS5E | $/hour |  |  | #DIV/0! |  |  |  | #DIV/0! | [6 empty] | #DIV/0! | [5 empty] | #DIV/0!
| SS5F | $/hour |  |  |  | #DIV/0! |  |  | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| SS5G | $/hour |  |  |  |  | #DIV/0! |  | #DIV/0! | [6 empty] | #DIV/0! | [7 empty] | #DIV/0!
| SS5H | $/hour | [5 empty] | #DIV/0! | #DIV/0! | [6 empty] | #DIV/0! | [8 empty] | #DIV/0! | #DIV/0!
4.6 Performance & Payment Bonds:
Performance & Payment Bonds (Total Costs, entire Project) | SS6B | See RFCSP | Total Est'd $Cost for Entire Project | 1 |  |  |  |  | 1 | [6 empty] | 0 | Total Cost Performance & Payment Bonds | 5 | n/a | 0 | 0
| SS6C | See RFCSP |  |  | 1 |  |  |  | 1 | [6 empty] | 0 | [5 empty] | 0
| SS6D | See RFCSP |  |  |  | 1 |  |  | 1 | [6 empty] | 0 | [6 empty] | 0
| SS6E | See RFCSP |  |  |  |  | 1 |  | 1 | [6 empty] | 0 | [7 empty] | 0
| SS6F | See RFCSP | [5 empty] | 1 | 1 | [6 empty] | 0 | [8 empty] | 0 | TRUE
4.7 Other SAWS Pricing Items:
Field Investigation, "Available Endpoint" (ref. SOW 2.10.3) | SS7J | per mtr | Per Meter Visit | 0 |  |  |  |  | 0 | [6 empty] | 0 | Field Investigations | 0 | 1% | 0 | 0
| SS7K | per mtr | Per Meter Visit |  | 0 |  |  |  | 0 | [6 empty] | 0 | [5 empty] | 0
| SS7L | per mtr | Per Meter Visit |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0
| SS7M | per mtr | Per Meter Visit |  |  |  | 0 |  | 0 | [6 empty] | 0 | [7 empty] | 0
| SS7N | per mtr | Per Meter Visit |  |  |  |  | 0 | 0 | [6 empty] | 0 | [8 empty] | 0 | TRUE
4.8 Other EPI Pricing Items (as defined by Respondent): |  |  |  | Estimated Install Qty by EPI (2023) | Estimated Install Qty by EPI (2024) | Estimated Install Qty by EPI (2025) | Estimated Install Qty by EPI (2026) | Estimated Install Qty by EPI (2027) | Total Estimated Install Qty by EPI | Included in Tabs 2 or 3? (Yes/No) (Note 6) | EPI's Unit Price (2023) | EPI's Unit Price (2024) | EPI's Unit Price (2025) | EPI's Unit Price (2026) | EPI's Unit Price (2027) | (Resulting) EPI's Extended Cost | Descr. | Total Qty | % | (Resulting) EPI's Extended Cost | 2023 | 2024 | 2025 | 2026 | 2027
[enter description] | SS8A | [7 empty] | 0 | [6 empty] | 0 | [enter description] | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[enter description] | SS8B | [7 empty] | 0 | [6 empty] | 0 | [enter description] | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[enter description] | SS8C | [7 empty] | 0 | [6 empty] | 0 | [enter description] | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[enter description] | SS8D | [7 empty] | 0 | [6 empty] | 0 | [enter description] | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[enter description] | SS8E | [7 empty] | 0 | [6 empty] | 0 | [enter description] | 0 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Total, All Services | [15 empty] | #DIV/0! |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Note 1: EPI's Installation Unit Pricing shall be fully loaded and include all field supervision & field quality audit labor; field installation workforce labor; photographs, fleet, tools and equipment, uniforms, safety equipment, et al; as specified in RFCSP.
Note 6: SAWS prefers that EPI provide these costs as separate line items as part of this Tab 4, Services & Support. Otherwise, if EPI indicates "Yes", then these costs are assumed to be included as part of its unit prices in Tabs 2 & 3.
Note 7: Price requested is for EPI to supply Field Installation Technician(s) to perform extra work, as specifically identified and approved from time-to-time by SAWS, if needed.
Note 8: Should EPI have or incur 1-Time costs associated with Mobilization or startup for this item, and if those costs are not already allocated as part of the EPI's Unit Costs for Meter Installation (Tab 2) and Other Equipment (Tab 3); then EPI shall include and allocate those costs evenly, as appropriate, across its monthly fees for the respective item.
Note 9: SAWS has extended the timeframe shown to provide payment for 1 month prior to start of initial installation ramp up to allow EPI vendor the opportunity to mobilize and put into place the services associated with this item.

## 5 Assumptions
Tab 5, Assumptions
Scenario 3: End Date 6.30.27
Respondent: | 0
Date | 0
Coding to be used for table
Yellow Cell inputs | Respondent's Information
Tab | Item | Assumptions

## 6 Meter Install Forecast-Est's
Appendix 6 - SAWS ConnectH2O AMI Meter Installation Forecast & Projections | [9 empty] | NO EPI VENDOR DATA ENTRY TO BE PERFORMED ON THIS SHEET. | [8 empty] | 0
Meter Installation Forecast & Projections
THESE METER COUNTS ARE BASED ON BEST INFORMATION CURRENTLY AVAILABLE. | [8 empty] | Scenario 3: End 6.30.27: |  |  | ESTIMATED INSTALLS BY METER SIZE AND YEAR.
THESE NUMBERS ARE, HOWEVER, SUBJECT TO VARIATION AND CHANGE. | [8 empty] | BASED ON INSTALLATION RUN RATES FROM TAB '2 FSWD Scenario 3, End 6.30.27'.
References to Meters herein includes installation of both Meters and their associated EndPoints.
[9 empty] | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | Totals
| 2022 | ALL | 5/8 - 2" | 3 - 10" | SAWS | Vendor | Vendor |  | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor | Vendor
Meter Size | Est'd Qty | Meters | Meters | Meters | Installs | Installs | Installs |  | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs | Installs
| note 3 | %'s | %'s | %'s | 5/8 - 2" | 5/8 - 2" | 3" - 10" |  | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 2" | 3" - 10" | 5/8 - 10"
5/8" | 498460.2232 | 87.59% | 87.94% |  | 42209.0434 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3/4" | 37140.2279 | 6.526% | 6.552% |  | 3144.9922 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1" | 15993.4658 | 2.81% | 2.821% |  | 1354.3084 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
1-1/2" | 8879.1273 | 1.56% | 1.566% |  | 751.8744 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
2" | 6374.4554 | 1.12% | 1.125% |  | 539.7816 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | TRUE
3" | 1114 | 0.1957% |  | 49.56% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
4" | 678 | 0.1191% |  | 30.16% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
6" | 337 | 0.05922% |  | 14.99% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
8" | 96 | 0.01687% |  | 4.27% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
10" | 23 | 0.004042% |  | 1.023% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Other | 0 | 0% |  | 0% |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | TRUE
Totals | 569095.4996 | 100% | 100% | 100% | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
[5 empty] | TRUE | TRUE | TRUE | 0 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
note 3: These are the estimated quantity of meters that exist & require replacement | [5 empty] | FALSE | FALSE
by EPI/SAWS, plus installation of new AMI communications modules, as of end of 1.31.23. | [5 empty] | Total: | 0 | FALSE | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | Total: | 0 | 0

## 2 FSWD Scenario 3, End 6.30.27
Full System Wide Deployment |  |  |  |  | 0 | FROM: | Appendix 6 - SAWS Connect H2O AMI Water Deployment Plan - | [7 empty] | Scenario 3: End Date 6.30.27
[7 empty] | References to Meters herein includes installation of both Meters and their associated EndPoints. | [7 empty] | EPI VENDOR To CUT 'N PASTE Yellow Cell data from its APPENDIX 6, Scenario 3.
| Yellow Cell: EPI Vendor to provide Data. | [9 empty] | EPI Vendor to Provide its planned # of Field Installers per Field Supervisor.
[6 empty] | 15 | [10 empty] | (EPI Contract Total Qty)
|  |  |  | Installs by Others - Actuals |  | SAWS Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  |  | EPI Vendor - New Installs - Planned |  |  | EPI Vendor - New Installs | TOTAL - ALL Installers - Planned |  |  | Qty Installs
|  |  |  | 5/8 - 2" Meters |  | 5/8 - 2" Meters Only |  |  |  | 5/8 - 2" Meters Only |  |  |  | 3" - 10" Meters Only (Note 1) |  |  | Total - All Meters | 5/8 - 10" Meters |  |  | by Year
| Mo-Yr | FSWD Deploy- ment Mo. # | Vendor Deploy- ment Mo. # | Avg. meters per month - all persons | Cumulative meters - all persons | Estimated Avg Installers per day | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. Number of Installers, this Month | Avg. meters per day - all persons | Avg. meters per month - all persons | Cumulative meters - all persons | Avg. meters per week - all Crews | Avg. meters per month - all persons | Cumulative meters - all persons | Cumulative meters - all persons | Total Avg. meters per day - all persons | Total Avg. meters per month - all persons | Cumulative Total meters - all persons | [Project Only; excludes New Bus. & Maint.]
AMI/MDMS | 2022-01-01
Phase 3 - FSWD | 2022-02-01
2022-03-01
2022-04-01
| 2022-05-01 | 1 |  | 1077 | 1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077 | 1077
| 2022-06-01 | 2 |  | 1989 | 3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989 | 3066
| 2022-07-01 | 3 |  | 3083 | 6149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083 | 6149
| 2022-08-01 | 4 |  | 6884 | 13033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6884 | 13033
| 2022-09-01 | 5 |  | 7774 | 20807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7774 | 20807
| 2022-10-01 | 6 |  | 3594 | 24401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3594 | 24401
| 2022-11-01 | 7 |  | 3194 | 27595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194 | 27595
| 2022-12-01 | 8 |  | 7160 | 34755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7160 | 34755 | 34755
AMI/MDMS | 2023-01-01 | 9 |  | 4702 | 39457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4702 | 39457
Phase 3 - FSWD | 2023-02-01 | 10 |  | 0 | 39457 | 13 | 195 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 43357
(cont'd) | 2023-03-01 | 11 |  | 0 | 39457 | 13 | 195 | 3900 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 47257
| 2023-04-01 | 12 |  | 0 | 39457 | 13 | 195 | 3900 | 11700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 51157
| 2023-05-01 | 13 |  | 0 | 39457 | 13 | 195 | 3900 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 55057
| 2023-06-01 | 14 |  | 0 | 39457 | 13 | 195 | 3900 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 58957
| 2023-07-01 | 15 |  | 0 | 39457 | 13 | 195 | 3900 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 62857
| 2023-08-01 | 16 |  | 0 | 39457 | 13 | 195 | 3900 | 27300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 66757
| 2023-09-01 | 17 |  | 0 | 39457 | 13 | 195 | 3900 | 31200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 70657
| 2023-10-01 | 18 |  | 0 | 39457 | 13 | 195 | 3900 | 35100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 74557
| 2023-11-01 | 19 | 1 | 0 | 39457 | 13 | 195 | 3900 | 39000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 78457
| 2023-12-01 | 20 | 2 | 0 | 39457 | 13 | 195 | 3900 | 42900 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 3900 | 82357 | 47602
AMI/MDMS | 2024-01-01 | 21 | 3 | 0 | 39457 | 7 | 105 | 2100 | 45000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 84457
Phase 3 - FSWD | 2024-02-01 | 22 | 4 | 0 | 39457 | 7 | 105 | 2100 | 47100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2100 | 86557
(cont'd) | 2024-03-01 | 23 | 5 | 0 | 39457 | 3 | 45 | 900 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 900 | 87457
| 2024-04-01 | 24 | 6 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-05-01 | 25 | 7 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-06-01 | 26 | 8 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-07-01 | 27 | 9 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-08-01 | 28 | 10 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-09-01 | 29 | 11 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-10-01 | 30 | 12 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-11-01 | 31 | 13 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2024-12-01 | 32 | 14 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 5100
AMI/MDMS | 2025-01-01 | 33 | 15 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2025-02-01 | 34 | 16 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2025-03-01 | 35 | 17 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-04-01 | 36 | 18 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-05-01 | 37 | 19 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-06-01 | 38 | 20 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-07-01 | 39 | 21 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-08-01 | 40 | 22 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-09-01 | 41 | 23 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-10-01 | 42 | 24 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-11-01 | 43 | 25 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2025-12-01 | 44 | 26 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2026-01-01 | 45 | 27 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2026-02-01 | 46 | 28 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2026-03-01 | 47 | 29 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-04-01 | 48 | 30 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-05-01 | 49 | 31 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-06-01 | 50 | 32 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-07-01 | 51 | 33 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-08-01 | 52 | 34 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-09-01 | 53 | 35 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-10-01 | 54 | 36 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-11-01 | 55 | 37 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2026-12-01 | 56 | 38 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457 | 0
AMI/MDMS | 2027-01-01 | 57 | 39 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
Phase 3 - FSWD | 2027-02-01 | 58 | 40 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
(cont'd) | 2027-03-01 | 59 | 41 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-04-01 | 60 | 42 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-05-01 | 61 | 43 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-06-01 | 62 | 44 | 0 | 39457 | 0 | 0 | 0 | 48000 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-07-01 | 63 | 45 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-08-01 | 64 | 46 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-09-01 | 65 | 47 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-10-01 | 66 | 48 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-11-01 | 67 | 49 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457
| 2027-12-01 | 68 | 50 | 0 | 39457 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87457 | 0
[7 empty] | Set-aside - Reserved | excludes | 53607 |  |  | EPI Vendor Qty Must Be: | 430800 |  | EPI Vendor Qty Must Be: | 2248 | 433048 |  |  |  | 87457
[7 empty] | SAWS Qty: | remaining | 48000 |  |  |  |  | Note 1: Option to assign these to |  |  | EPI Total Qty Must Be: 433,048 |  |  | Set-aside - Reserved | 53607
[14 empty] | EPI is at SAWS' Discretion. | [5 empty] | Total | 141064
Start no earlier than Sep-24
Start Ramp in Nov-23