## Master
SAN ANTONIO WATER SYSTEM | [6 empty] | SAMPLE
PROJECT CONSTRUCTION PROGRAM
CONSTRUCTION ESTIMATE CERTIFICATION FORM PAYMENT ESTIMATE No: | [6 empty] | 2 (entered on page 1 only)
Project: | Project Title (entered on page 1 only) |  |  | Date: |  | 2001-10-01
00-0000 (Water) (entered on page 1 only)
| 11-1111 (Sewer) (entered on page 1 only) |  |  | For Period: |  | 2001-09-01 | to | 2001-09-30
Payable To: | Contractor Name (entered on page 1 only)
Contractor Address (entered on page 1 only)
Contractor City, State, Zip (entered on page 1 only)
Design Engineer: | Name of Consultant or Engineer (entered on page 1 only)
Original Water Contract Amount: |  |  | 74702.56
Original Sewer Contract Amount: |  |  | 238013.45
Change Order(s) Approved: |  |  | 22000
Total Contract Amount: |  |  | 334716.01
Change Order Percentage |  |  | 7.035%
% Complete
To Date
Total Water Work Completed to Date on Original Bids: | [5 empty] | 43843.65 |  | 58.69%
Total Sewer Work Completed to Date on Original Bids: | [5 empty] | 118528.35 |  | 49.8%
Change Orders Completed: | [5 empty] | 14250 |  | 64.77%
Materials Stored on Site: | [5 empty] | 4329.5 |  | NA
Total Value of Work To Date: | [5 empty] | 180951.5 |  | 54.06%
Less 5% Retained: | [5 empty] | 9047.575
Less Previous Payment(s): | [5 empty] | 120000
Amount Due This Period: | [5 empty] | 51903.925
Certification is hereby made that this estimate is true and correct and eligible for payment
1 |  |  |  | 4
Contractor |  | Date |  | Manager, Construction |  |  |  | Date
2 |  |  |  | 5
Construction Inspector / Observer |  | Date |  | Director, Major Projects |  |  |  | Date
(If monthly invoice over $100,000)
3
Area Supervisor / Inspection Engineer |  | Date
6 |  |  |  | 1A
Manager, Contract Administration |  | Date |  | Design Consultant @ semi-final invoice only |  |  |  | Date
For routine invoices, consultant will be provided a copy
FOR SAWS INTERNAL USE
7. Property Records (for capitalization) |  |  | 8. Accounts Payable (for accounting) |  |  |  | 9. Treasury (for payment)
SAWS payment period is NLT 30 days after invoice receipt at Construction Inspection office to date of check or electronic funds transfer.
Note: Blue fields are contractor inputed / updated each month.
Note: The information / data on these sheets are for example only. The forms must be modified for each contract.
SAN ANTONIO WATER SYSTEM | [6 empty] | SAMPLE
PROJECT CONSTRUCTION PROGRAM
CONSTRUCTION ESTIMATE CERTIFICATION FORM PAYMENT ESTIMATE No: | [6 empty] | 2 (entered on page 1 only)
(CONTINUATION SHEET)
Project: | Project Title (entered on page 1 only) |  |  | Project #: |  | 11-1111 (Sewer) (entered on page 1 only)
Contractor: | Contractor Name (entered on page 1 only)
Design Engineer: | Name of Consultant or Engineer (entered on page 1 only)
[6 empty] | Amount | Amount
Item |  |  | Original | Unit |  | Completed | Completed | Dollar
No. | Description | Unit | Quantity | Price |  | This Period | To Date | Total
101 | Mobilization | LS | 1 | 51000.17 | 51000.17 | 0.9 | 0.9 | 45900.15
550 | San Sew Trench Protection | ft | 3939 | 1 | 3939 | 645 | 1000 | 1000
848 | San Sew (8 in) | ft | 158 | 16.75 | 2646.5 | 95 | 125 | 2093.75
848 | San Sew(12 in) | ft | 1158 | 18.25 | 21133.5 | 500 | 775 | 14143.75
854 | San Sew(6 in) (Lateral Pipe) | ft | 385 | 10.8 | 4158 | 0 | 0 | 0
848 | San Sew(4 in) (Force Main) | ft | 2238 | 18.5 | 41403 | 50 | 100 | 1850
852 | San Sew(MH Compl) | EA | 19 | 1516.06 | 28805.14 | 2 | 5 | 7580.3
804 | San Sew(Select Bedding) | cyd | 135 | 26.51 | 3578.85 | 75 | 85 | 2253.35
858 | San Sew(Concrete Encasement) | cyd | 5 | 147.53 | 737.65 | 1 | 3 | 442.59
858 | San Sew(Conrete Cradles) | cyd | 4.5 | 151.32 | 680.94 | 2 | 3 | 453.96
511 | San Sew(Cut & Restore Pavement) | syd | 690 | 39.03 | 26930.7 | 225 | 350 | 13660.5
890 | Sanitary Sew Lift Sta. (A) | LS | 1 | 26500 | 26500 | 0.25 | 0.5 | 13250
890 | Sanitary Sew Lift Sta. (B) | LS | 1 | 26500 | 26500 | 0.25 | 0.6 | 15900
| Total Amount |  | Bid | 238013.45 |  |  | To Date | 118528.35
SAN ANTONIO WATER SYSTEM | [6 empty] | SAMPLE
PROJECT CONSTRUCTION PROGRAM
CONSTRUCTION ESTIMATE CERTIFICATION FORM PAYMENT ESTIMATE No: | [6 empty] | 2 (entered on page 1 only)
(CONTINUATION SHEET)
Project Title | Project Title (entered on page 1 only) |  |  | Project #: |  | 00-0000 (Water) (entered on page 1 only)
Contractor: | Contractor Name (entered on page 1 only)
Design Engineer: | Name of Consultant or Engineer (entered on page 1 only)
[6 empty] | Amount | Amount
Item |  |  | Original | Unit |  | Completed | Completed | Dollar
No. | Description | Unit | Quantity | Price |  | This Period | To Date | Total
100 | Mobilization | LS | 1 | 20477.34 | 20477.34 | 0.5 | 0.8 | 16381.87
826 | Adjust Exist Valve Box | EA | 8 | 161.76 | 1294.08 | 3 | 5 | 808.8
511 | Cut & Replace Asph Pavement | syd | 120 | 38.11 | 4573.2 | 11.5 | 15.3 | 583.08
550 | Trench Excavation Prtctn | ft | 1353 | 1 | 1353 | 500 | 650 | 650
818 | 8 in PVC Wtr Main | ft | 1353 | 18.75 | 25368.75 | 500 | 650 | 12187.5
828 | 8 in Gate Valve & Box | EA | 8 | 971.91 | 7775.28 | 3 | 5 | 4859.55
840 | 6 in Tie-in | EA | 3 | 649.68 | 1949.04 | 1 | 2 | 1299.36
840 | 8 in Tie-in | EA | 1 | 665.11 | 665.11 | 1 | 1 | 665.11
834 | Std. FH w/6 in Valve & Box | EA | 4 | 1739.74 | 6958.96 | 1 | 2 | 3479.48
844 | 2 in (Temporary Blow-Off) | EA | 4 | 679.45 | 2717.8 | 1 | 2 | 1358.9
844 | 2 in (Permanent Blow-off) | EA | 2 | 785 | 1570 | 1 | 2 | 1570
| Total Amount |  | Bid | 74702.56 |  |  | To Date | 43843.65
SAN ANTONIO WATER SYSTEM | [6 empty] | SAMPLE
PROJECT CONSTRUCTION PROGRAM
CONSTRUCTION ESTIMATE CERTIFICATION FORM PAYMENT ESTIMATE No: | [6 empty] | 2 (entered on page 1 only)
(CONTINUATION SHEET)
Project: | Project Title (entered on page 1 only) |  |  | Project #s: |  | 00-0000 (Water) (entered on page 1 only)
11-1111 (Sewer) (entered on page 1 only)
Contractor: | Contractor Name (entered on page 1 only)
Design Engineer: | Name of Consultant or Engineer (entered on page 1 only)
[6 empty] | Amount | Amount
Item |  |  | Original | Unit |  | Completed | Completed
No. | Description | Unit | Quantity | Price |  | This Period | To Date | Total
Water
1 | Add Extra Work | LS | 1 | 5000 | 5000 | 0.5 | 0.75 | 3750
2 | Add More Work | LS | 1 | 2000 | 2000 | 0.1 | 0.3 | 600
| Total Water Change Orders |  |  | 7000 |  |  |  | 4350
Sewer
1 | Add Extra Work | LS | 1 | 3000 | 3000 | 0.2 | 0.5 | 1500
2 | Add Lots More Work | LS | 1 | 12000 | 12000 | 0.5 | 0.7 | 8400
| Total Sewer Change Orders |  |  | 15000 |  |  |  | 9900
| TOTAL CHANGE ORDERS |  |  | 22000 |  |  |  | 14250
22000
Change Orders Approved
14250
Change Orders Completed
|  | ATTACHMENT TO |  |  |  |  | SAMPLE
|  | PARTIAL PAYMENT NO. |  |  |  | 2 (entered on page 1 only)
11-1111 (Sewer) (entered on page 1 only)
00-0000 (Water) (entered on page 1 only)
INVENTORY OF
MATERIALS ON-SITE
Project: | Project Title (entered on page 1 only)
|  |  | Invoiced | Material |  |  | Cost
Item |  | Unit | Quantity | On Hand |  |  | Per Unit | Total
00-0000 (Water) (entered on page 1 only)
8" PVC Water Pipe |  | ft | 1353 | 703 |  |  | 2.5 | 1757.5
11-1111 (Sewer) (entered on page 1 only)
8" Sewer Pipe |  | ft | 158 | 33 |  |  | 2.5 | 82.5
12" Sewer Pipe |  | ft | 1158 | 383 |  |  | 6.5 | 2489.5
|  |  |  | TOTAL MATERIALS ON-SITE |  |  |  | 4329.5
Contractor | [5 empty] | Date
Construction Inspector / Observer | [5 empty] | Date
NOTE: If more than one page for Materials Stored On Site, Contractor and Inspector / Observer must review and sign each page.